## PEARS
Program Evaluation and Reporting System (PEARS)
Project Manager: Carolyn Rider (cdrider@ucanr.edu)
For questions, contact: EvaluateSNAPEd@ucanr.edu
Activities | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct
First Quarter Data Entry & Quality Assurance | Oct: Gray cells denote all months for activity; X denotes a deadline.
Enter all activities targeting SNAP-Ed audience into PEARS PSE, Program Activities, & Indirect Activities modules as they occur. Ensure reporting is current by end of quarter. | bar: Oct to Dec
Enter partnership and coalition participation into the appropriate modules as they occur. Copy ongoing activities from prior year. Ensure reporting is current by end of quarter. | bar: Oct to Dec
Review and resolve issues flagged by NPI for Quarter 1 and update status in Issue File. | bar: Feb to Mar
Second Quarter Data Entry & Quality Assurance | Oct: Gray cells denote all months for activity; X denotes a deadline.
Enter all activities targeting SNAP-Ed audience into PEARS PSE, Program Activities, & Indirect Activities modules as they occur. Ensure reporting is current by end of quarter. | bar: Jan to Mar
Enter partnership and coalition participation into the appropriate modules as they occur and no later than the end of the quarter. Ensure reporting is current by end of quarter. | bar: Jan to Mar
Review and resolve issues flagged by NPI for Quarter 2 and update status in Issue File. | bar: May to Jun
Third Quarter Data Entry & Quality Assurance | Oct: Gray cells denote all months for activity; X denotes a deadline.
Enter all activities targeting SNAP-Ed audience into PEARS PSE, Program Activities, & Indirect Activities modules as they occur. Ensure reporting is current by end of quarter. | bar: Apr to Jun
Enter partnership and coalition participation into the appropriate modules as they occur and no later than the end of the quarter. Ensure reporting is current by end of quarter. | bar: Apr to Jun
Review and resolve issues flagged by NPI for Quarter 3 and update status in Issue File. | bar: Aug to Sept
Fourth Quarter Data Entry & Quality Assurance | Oct: Gray cells denote all months for activity; X denotes a deadline.
Enter all activities targeting SNAP-Ed audience into PEARS PSE, Program Activities, & Indirect Activities modules as they occur. Ensure reporting is complete by end of quarter. | bar: Jul to Oct
Enter partnership and coalition participation into the appropriate modules as they occur and no later than the end of the quarter. Ensure reporting is complete by end of quarter. | bar: Jul to Oct
Review and resolve issues flagged by NPI for Quarter 4 and update status in Issue File. | bar: Sept to Oct
Respond, as needed, to year-end QA/QC emails sent by NPI by making appropriate revisions to data in PEARS. | bar: Oct
Year-End Data Entry & Quality Assurance | Oct: Gray cells denote all months for activity; X denotes a deadline.
Create at least one PSE-related Success Story by the annual reporting deadline. | bar: Oct to Oct
Finalize data entry and quality assurance and mark all entries complete. | bar: Oct to Oct
Respond, as needed, to year-end QA/QC emails sent by NPI so that state data managers can make appropriate revisions to data in PEARS. | bar: Oct

## Assessment Questionnaires
Assessment Questionnaires: Site-Level (SLAQ), Organization-Level (OAQ) and LHD Activity Checklist (LAC)
Project Manager: Janice Kao (jankao@ucanr.edu)
For questions, contact: EvaluateSNAPEd@ucanr.edu
SLAQs and OAQs are for schools, school districts, OST, ECE, and retail sites that are already engaged CFHL partners and have agreed to implement PSE changes.
Gray cells denote typical months for activity; X denotes a deadline.
Activities | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Learn setting SLAQ Administration (schools, ECE, and OST sites)
Determine which sites will need a SLAQ for the upcoming FFY.
Prepare to conduct SLAQs by reviewing protocols and resources. Identify contacts for each site to facilitate SLAQ completion and share site protocols and questionnaires. Updated SLAQs and protocols are released each July for the upcoming FFY.
Collect completed SLAQs, before PSE changes are implemented for the year. They only need to be conducted once within a year.
Enter and submit completed SLAQs into Survey 123 and receive scores. Entries are due June 30 for the current FFY. (Example: All FFY 25 entries are due June 30, 2025) | bar: Gray cells denote typical months for activity; X denotes a deadline. Jun
Use SLAQ and LEAP results and scores to plan your activities. Action planning tools are available here: https://ucanr.edu/sites/slaq/Resources/
Communicate LEAP results with sites. Share certificates and digital promotions package materials with sites, and use the digital promotions package to celebrate successes.
OAQ Administration (school districts)
Determine which school districts will need an OAQ for the upcoming FFY.
Prepare to conduct OAQs by reviewing protocols and resources; identify contacts for each district to facilitate OAQ completion, share protocols, and check in about the WellSAT Policy tool. Updated materials are released each July for the upcoming FFY.
Check that a WellSAT Policy tool has been completed for each district since their last wellness policy update and within the last 3 years. If not, work with district contact(s) to complete WellSAT Policy tool.
Collect completed OAQs, before PSE changes are implemented for the year. Ensure that WellSAT Policy tool scores are included on completed OAQs.
Enter and submit completed OAQs into Survey 123 and receive scores. Entries are due June 30 for current FFY. (Example: All FFY 25 entries are due June 30, 2025) | bar: Gray cells denote typical months for activity; X denotes a deadline. Jun
Use OAQ results and scores to plan your activities. Action planning tools are available here: https://ucanr.edu/sites/slaq/Resources/
Food Retail SLAQ Administration
Determine which stores will need a SLAQ for the upcoming FFY.
Prepare to conduct SLAQs by reviewing protocols and resources. Identify and train data collectors to conduct store observations and manager interviews; share SLAQ forms, protocols and other materials. Updated SLAQs and protocols are released each July for the upcoming FFY.
Collect completed SLAQs, before PSE changes are implemented for the year. They only need to be conducted once within a year.
Enter and submit completed SLAQs into Survey 123 and receive scores. Entries are due August 31 for the current FFY. (Example: All FFY 25 entries are due August 31, 2025) | bar: Gray cells denote typical months for activity; X denotes a deadline. Aug
Use SLAQ results and scores to plan your activities. Action planning tools are available here: https://ucanr.edu/sites/slaq/Resources/
LHD Activity Checklist (LAC) Completion -- 1 LAC per SLAQ and OAQ (all settings)
Begin completing the LHD Activity Checklist (LAC) to track CFHL activities at each SLAQ site and OAQ district. Updated ACs are released in January each year.
Enter completed LACs into Survey 123 once all your CFHL activities have finished for the year. Entries are due Oct 15 for previous FFY. (Example: All FFY 25 entries are due Oct 15, 2025) | bar: Gray cells denote typical months for activity; X denotes a deadline. Oct
SLAQ/OAQ Reporting in PEARS (all settings)
Report your most recent SLAQ and OAQ results in PEARS (PSE module, Needs Assessments section). LACs do not need to be reported in PEARS. Job aid available here: https://www.cdss.ca.gov/inforesources/pears | bar: Gray cells denote typical months for activity; X denotes a deadline. Oct
Note on A13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should we add one or two LEAP-related items here? I think I would modify the one on line 14 about action planning to say "Use SLAQ and LEAP results and scores..." Then I would add a line about sharing LEAP certificates with sites and using the digital promotions package to promote awards. Is there anything else to add? Reply: I thought about that too (adding LEAP items here) — please feel free, if you still want to! Reply: Done! I highlighted just Sept-Nov gray for communicating LEAP/using digital promotions, but honestly I'm not sure what makes most sense. Thoughts on that? Reply: I think that’s good! I think we explained “gray” as recommended time frames Reply: okay, then I'll mark this comment resolved!

## IOE
Impact Outcome Evaluation (IOE)
Project Manager: Amanda Linares (amlinares@ucanr.edu, 916-200-5188)
For questions, contact: Amanda Linares (amlinares@ucanr.edu, 916-200-5188)
Activities | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
Planning | Aug: Gray cells denote all months for activity; X denotes a deadline.
Engage intervention site(s); any school or school-based afterschool serving grades 4-12 | bar: Aug to Sept; May to Jul
Attend EATS Survey Administration training (annually) | bar: Aug; Jul
Provide Amanda with a completed Planning Worksheet to receive school-specific EATS online pre/post links | bar: Aug to Oct; Jul
Prior to Pre-testing | Aug: Gray cells denote all months for activity; X denotes a deadline.
Send home Parent Opt Out Forms 2 weeks prior to pre-testing | bar: Aug to Oct
Pre-testing | Aug: Gray cells denote all months for activity; X denotes a deadline.
Administer EATS with at least 2 classrooms of students per school (goal = 30 matched pre/post-tests in each school) | bar: Aug to Oct
Intervention Implementation | Aug: Gray cells denote all months for activity; X denotes a deadline.
Conduct intervention | bar: Sept to May
Post-testing | Aug: Gray cells denote all months for activity; X denotes a deadline.
Administer EATS to all students who received the pre-test | bar: Apr to Jun
Data Entry | Aug: Gray cells denote all months for activity; X denotes a deadline.
If EATS online was used, there will be no data entry; if paper surveys were used, pre-tests should be entered into the school-specific survey links | bar: Aug to Oct
If EATS online was used, there will be no data entry; if paper surveys were used, post-tests should be entered into the school-specific survey links | bar: Apr to Jun
End of Year (June 30th) Deliverables | Aug: Gray cells denote all months for activity; X denotes a deadline.
To Amanda: 1) Pre/post tests entered online (for paper) 2) Planning Workshseet with updates (accurate pre/post dates and opt out data) | bar: Jun

## Adult Direct Ed Evaluation
Adult Direct Education Evaluation
Project Manager: Amanda Linares (amlinares@ucanr.edu, 916-200-5188)
For questions, contact: Amanda Linares (amlinares@ucanr.edu, 916-200-5188)
Activities | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Yearly Survey Closure/Downtime | Sept: Gray cells denote all months for activity; X denotes a deadline.
The CalFresh Healthy Living Adult Survey closes annually on 8/31 and does not reopen until the first day of PEARS (mid-October). Evaluation does not need to occur for any direct education in this closure period. | bar: Sept
Planning | Sept: Gray cells denote all months for activity; X denotes a deadline.
Attend Survey Administration training (annually) | bar: Sept
Enter Program Activity* into PEARS before administering Pre-test
Pre-testing, Intervention Implementation, Post-testing | Sept: Gray cells denote all months for activity; X denotes a deadline.
Administer the CalFresh Healthy Living Adult pre-test before delivering a direct education series of four or more sessions
Administer direct education series of four or more sessions over at least four weeks.
Administer the CalFresh Healthy Living Adult post-test after delivering a direct education series of four or more sessions
Data Entry | Sept: Gray cells denote all months for activity; X denotes a deadline.
If online CalFresh Healthy Living Adult Survey was used, there will be no data entry; if paper surveys were used, pre/post-tests should be entered into Survey123 by Aug 31st. | bar: Oct to Aug
End of Year (August 31st) Deliverables | Sept: Gray cells denote all months for activity; X denotes a deadline.
To Amanda: 1) Pre/post tests entered online (for paper) | bar: Aug
*Series-based direct education should only utilize one program activity ID (i.e., sessions are batched in a single entry). Surveys cannot be matched without matching Program Activity IDs at pre- and post-test.