## IOE
Impact Outcome Evaluation (IOE)
Project Manager/Main Point of Contact: Amanda Linares (amlinares@ucanr.edu, 916-200-5188)
Activities | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
Planning | bar: Sept to Jun
Engage or re-engage intervention and comparison site(s) | bar: Aug; Jul
Complete/update FFY 20-22 Planning Worksheet and return to Amanda; upon receipt, Amanda will provide EATS online survey links for each site | bar: Aug to Sept; Jul
Annual check-in with Amanda | bar: Aug to Sept
Pretesting
Administer EATS with 60+ 4th and/or 5th grade students in school (intervention and comparison) or after school (intervention) sites | bar: Aug to Nov
At pre-test, collect data necessary to complete the Attrition Log | bar: Aug to Nov
Collect a SLAQ from all intervention and comparison sites using the appropriate tool (elementary or OST SLAQ) | bar: Aug to Nov
Intervention Implementation
Conduct intervention consisting of direct education and PSE in intervention elementary school and after school sites | bar: Aug to Apr
Post-testing
Administer EATS with 60+ 4th and/or 5th grade students in school (intervention and comparison) or after school (intervention) sites | bar: Mar to Jun
At post-test, collect data necessary to complete the Attrition Log | bar: Mar to Jun
Data Entry
Enter school SLAQs into Survey 123 (LHD does this, not school site); either enter OST SLAQs into Survey123 OR the OSTsite can do it; send autogenerated score report to Amanda | bar: Mar to Jun
If EATS online was used, there will be no data entry; if paper surveys were used, pre/post-tests should be entered into the site-specific survey link. | bar: Aug to Jun
End of Year (July 30th) Deliverables
To Amanda: 1) Provide autogenerated SLAQ score reports 2) Confirm receipt of pre/post-tests in Qualtrics 3) Provide Attrition Log 3) Provide Planning Worksheet updated through end of year | bar: Jul

## SLAQ & LAC
Site-level Assessment Questionnaire (SLAQ)
Main Contact: EvaluateSNAPEd@ucanr.edu | Link to SLAQs and LACs: https://ucanr.edu/sites/SLAQ/SLAQ_Questionnaires/
Project Manager: Janice Kao (jankao@ucanr.edu, 510-987-0613)
Other Staff on Project: Christina Becker (cmbecker@ucanr.edu), Carolyn Rider (cdrider@ucanr.edu), Amanda Linares (amlinares@ucanr.edu)
Activities | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
SLAQ Administration | bar: Sept to Jun
Collect completed SLAQs from school, OST, ECE, retail within the same timeframe annually (unless an alternate situation has been agreed upon) | bar: Aug to Oct; May to Jul
Enter and submit completed SLAQs into Survey 123 and receive scores | bar: Aug to Oct; May to Jul
Use SLAQ results and scores to plan your activities | bar: Aug to Mar
SLAQ LAC Completion
Enter and submit the SLAQ LHD Activity Checklist (LAC) into Survey 123 once CFHL activities are complete and before end of federal fiscal year | bar: Aug to Sept; Apr to Jul
SLAQ Reporting
Annually report on SLAQ results in the PEARS PSE module, in the Needs Assessments section. Job aid available here: https://ucanr.edu/sites/CDPH_PEARS/Tools_Resources/ | bar: Aug to Oct; May to Jul

## PEARS
Program Evaluation and Reporting System (PEARS)
Project Manager: Carolyn Rider (cdrider@ucanr.edu, carolyn.rider@cdph.ca.gov)
Main Point of Contact: EvaluateSNAPEd@ucanr.edu
Other Staff on Project: Janice Kao (jankao@ucanr.edu), Evan Talmage (etalmage@ucanr.edu), Christina Becker (cmbecker@ucanr.edu)
Activities | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept
Training and Technical Assistance
Attend PEARS training as offered by KSU, CDSS, or NPI. | bar: Oct to Sept
Stay informed about PEARS reporting updates via monthly newsletter. | bar: Oct to Sept
Data Entry
Enter all activities targeting SNAP-Ed audience into PEARS PSE, Program Activities, and Indirect Activities module as they are completed. | bar: Oct to Sept
Enter partnership and coalition data into the appropriate modules. | bar: Oct to Sept
Create at least one PSE-related Success Story by the end of the year. | bar: Oct to Sept
Annually report on SLAQ results in the PEARS PSE module, in the Needs Assessments section. Job aid available here: https://ucanr.edu/sites/CDPH_PEARS/Tools_Resources/ | bar: Oct to Dec
Data Quality Assurance
Periodically review data entered by staff and contractors under your supervision. | bar: Oct to Sept
Respond, as needed, to QA/QC emails sent by state reviewers by making appropriate revisions to data in PEARS. | bar: Oct to Sept